Short Paper:

Work Breakdown Structure for the

Redevelopment of the Sanford B. Ladd School

Jennifer Lakey
Southern New Hampshire University
QSO 440: Project Management
Dr. Jillian Zambon
May 23, 2026

Short Paper: Work Breakdown Structure for the

Redevelopment of the Sanford B. Ladd School

Developing a Work Breakdown Structure (WBS) is an essential part of defining project scope and organizing the major components of a complex initiative. For the redevelopment of the Sanford B. Ladd School into a community resource hub, the WBS provides a structured hierarchy that supports planning, coordination, and accountability across construction, environmental review, community engagement, and program development. Because the project involves historic preservation, federal grant compliance, and significant building rehabilitation, a clear WBS is necessary to manage parallel workstreams and ensure alignment with regulatory and funding requirements (City of Kansas City, Missouri, 2024; U.S. Department of Housing and Urban Development, 2023; U.S. Economic Development Administration, 2023). The WBS also reflects the technical and architectural considerations documented in the Ladd School redevelopment materials, which guide the scope of renovation and site improvements (Drexel Tech, 2026; LocalCode, n.d.). By decomposing the project into phases, work packages, and activities, the WBS establishes the foundation for effective scope management and supports the development of realistic schedules, resource plans, and performance expectations.

To illustrate the full scope of the redevelopment effort, the following text-based Work Breakdown Structure (WBS) outline presents the project in a hierarchical format that organizes phases, work packages, and activities.

Work Breakdown Structure (WBS) Outline

Project: Redevelopment of the Sanford B. Ladd School into a Community Resource Hub

1.0 Pre-Development Phase

1.1 Community Engagement

1.1.1 Conduct neighborhood listening sessions

1.1.2 Conduct interest gauge / pre-recruitment drive

1.1.3 Facilitate stakeholder interviews

1.1.4 Compile community needs assessment

1.2 Governance Formation

1.2.1 Establish community steering committee

1.2.2 Develop cooperative or land trust framework

1.2.3 Approve governance charter

1.3 Funding and Grant Preparation

1.3.1 Prepare HUD CDBG application

1.3.2 Prepare CCED Sales Tax grant application

1.3.3 Prepare EDA Public Works grant application

1.4 Environmental & Architectural Preparation

1.4.1 Conduct environmental review and testing

1.4.2 Conduct structural analysis and landscape analysis

1.4.3 Complete architectural and landscape schematic design

1.4.4 Finalize construction documents

2.0 Building Renovation Phase

2.1 Site Preparation & Abatement

2.1.1 Perform hazardous materials abatement

2.1.2 Complete selective demolition

2.1.3 Secure site and install temporary utilities

2.2 Exterior Restoration

2.2.1 Repair masonry and façade

2.2.2 Replace or restore windows and doors

2.2.3 Repair roofing and drainage systems

2.3 Mechanical, Electrical, and Plumbing (MEP)

2.3.1 Install HVAC systems

2.3.2 Upgrade electrical service and wiring

2.3.3 Replace plumbing and install fixtures

2.4 Interior Construction & Finishes

2.4.1 Build interior walls and program spaces

2.4.2 Install flooring, ceilings, and finishes

2.4.3 Install technology infrastructure and equipment

2.5 Final Inspections & Occupancy

2.5.1 Conduct code compliance inspections

2.5.2 Complete punch list corrections

2.5.3 Obtain certificate of occupancy

3.0 Community Garden Development

3.1 Site Preparation

3.1.1 Clear and grade elevated field

3.1.2 Install/repair fencing and access paths

3.2 Garden Construction

3.2.1 Build raised garden beds

3.2.2 Install irrigation system

3.2.3 Deliver soil and compost

3.3 Community Planting

3.3.1 Organize volunteer planting days

3.3.2 Plant initial crops

3.3.3 Set up maintenance schedule

4.0 Administrative & Program Development (Parallel Workstream)

4.1 Staffing & Volunteer Recruitment

4.1.1 Recruit educators and program staff

4.1.2 Recruit volunteers for pantry and garden

4.1.3 Conduct background checks and onboarding

4.2 Program & Partnership Development

4.2.1 Finalize partnership with Parks & Recreation

4.2.2 Finalize partnership with Kansas City Public Library

4.2.3 Develop curricula for job training and community education

4.2.4 Coordinate donation drives

4.3 Operational Readiness

4.3.1 Develop policies and procedures

4.3.2 Create safety and emergency plans

4.3.3 Prepare opening-day operations plan

5.0 Project Closeout

5.1 Grand Opening

5.1.1 Coordinate opening event

5.1.2 Launch job center and programming

5.1.3 Launch pantry and closet

5.1.4 Celebrate first garden harvest

The Microsoft Project image that follows provides a detailed software-based representation of the hierarchical WBS outlined in the preceding text. While the written outline presents the project’s phases, work packages, and activities at a structural level, the Microsoft Project version expands each element with durations, predecessors, resources, and responsibility assignments to support schedule development and critical path analysis. This enhanced level of detail ensures that the WBS functions not only as a scope definition tool but also as a fully integrated project management artifact that aligns the written structure with its operational implementation.

Figure 1

Work Breakdown Structure for the Sanford B. Ladd School Redevelopment Project

Conclusion

The completed WBS provides a structured representation of the major deliverables required to transform the Sanford B. Ladd School into a functional community resource hub. By breaking the project into detailed activities across pre-development, renovation, garden construction, and administrative preparation, the WBS strengthens scope clarity and supports the coordination of work that must comply with federal funding guidelines and local redevelopment requirements (City of Kansas City, Missouri, 2024; U.S. Economic Development Administration, 2023). This level of decomposition also aligns with the technical expectations outlined in the project’s architectural and environmental documentation, ensuring that the redevelopment effort remains grounded in realistic construction and design parameters (Drexel Tech, 2026; LocalCode, n.d.). In addition, the expanded WBS developed in Microsoft Project incorporates durations, dependencies, and resource assignments, allowing the project team to validate sequencing, identify the critical path, and confirm that the 36 to 38 month timeline established in the proposal is achievable. As the project progresses, the WBS will serve as a reference point for monitoring performance, managing risks, and ensuring that all components of the redevelopment effort remain aligned with community needs and long-term goals.

References

City of Kansas City, Missouri. (2024). Central City Economic Development (CCED) Sales Tax program guidelines. https://www.kcmo.gov

Drexel Tech. (2026). Ladd School redevelopment: 100% CD set. https://planroom.drexeltech.com/projects/342/details/ladd-school-redevelopment-100-cd-set-kansas-city-mo

LocalCode. (n.d.). Ladd School redevelopment overview. https://www.localcode.co/ladd

U.S. Department of Housing and Urban Development. (2023). Community Development Block Grant program: CDBG basics. https://www.hud.gov/program_offices/comm_planning/communitydevelopment/programs

U.S. Economic Development Administration. (2023). Public Works and Economic Adjustment Assistance programs. https://www.eda.gov/funding/programs

WBS Dictionary

Project: Redevelopment of the Sanford B. Ladd School into a Community Resource Hub

1.0 Pre Development Phase

1.1 Community Engagement

1.1.1 Conduct neighborhood listening sessions
Facilitate open meetings to gather resident input on needs, priorities, and concerns.

1.1.2 Conduct interest gauge / pre-recruitment drive
Assess community interest in participation and identify potential volunteers or program contributors.

1.1.3 Facilitate stakeholder interviews
Interview key community leaders, partner organizations, and local agencies to refine project goals.

1.1.4 Compile community needs assessment
Synthesize engagement findings into a formal report that informs design and program decisions.

1.2 Governance Formation

1.2.1 Establish community steering committee
Form a representative body responsible for oversight and decision making.

1.2.2 Develop cooperative or land trust framework
Define the ownership and governance structure for long-term community control.

1.2.3 Approve governance charter
Finalize and adopt the charter outlining roles, responsibilities, and operational guidelines.

1.3 Funding and Grant Preparation

1.3.1 Prepare HUD CDBG application
Develop and submit the Community Development Block Grant proposal.

1.3.2 Prepare CCED Sales Tax grant application
Prepare the application for the Central City Economic Development Sales Tax program.

1.3.3 Prepare EDA Public Works grant application
Complete the Economic Development Administration grant submission for capital funding.

1.4 Environmental and Architectural Preparation

1.4.1 Conduct environmental review and testing
Perform assessments required for compliance with environmental regulations.

1.4.2 Conduct structural and landscape analysis
Evaluate building integrity and site conditions to inform design decisions.

1.4.3 Complete architectural and landscape schematic design
Develop preliminary design concepts for interior, exterior, and site improvements.

1.4.4 Finalize construction documents
Produce detailed drawings and specifications required for permitting and construction.

2.0 Building Renovation Phase

2.1 Site Preparation and Abatement

2.1.1 Perform hazardous materials abatement
Remove asbestos, lead, and other hazardous materials in compliance with safety standards.

2.1.2 Complete selective demolition
Remove deteriorated or obsolete interior and exterior elements.

2.1.3 Secure site and install temporary utilities
Set up fencing, lighting, and temporary power to support construction activities.

2.2 Exterior Restoration

2.2.1 Repair masonry and façade
Restore brickwork, stone, and exterior surfaces to preserve structural integrity.

2.2.2 Replace or restore windows and doors
Install energy efficient or historically appropriate openings.

2.2.3 Repair roofing and drainage systems
Ensure the building envelope is weather tight and properly drained.

2.3 Mechanical, Electrical, and Plumbing (MEP)

2.3.1 Install HVAC systems
Install modern heating, ventilation, and air conditioning systems.

2.3.2 Upgrade electrical service and wiring
Replace outdated wiring and increase electrical capacity.

2.3.3 Replace plumbing and install fixtures
Install new piping, restrooms, and water service components.

2.4 Interior Construction and Finishes

2.4.1 Build interior walls and program spaces
Construct classrooms, offices, labs, and multipurpose areas.

2.4.2 Install flooring, ceilings, and finishes
Complete interior finishes consistent with program needs.

2.4.3 Install technology infrastructure and equipment
Set up office, networking, computer labs, and audiovisual systems.

2.5 Final Inspections and Occupancy

2.5.1 Conduct code compliance inspections
Coordinate inspections with local authorities to verify compliance.

2.5.2 Complete punch list corrections
Address remaining deficiencies identified during walkthroughs.

2.5.3 Obtain certificate of occupancy
Secure official approval for building use.

3.0 Community Garden Development

3.1 Site Preparation

3.1.1 Clear and grade elevated field
Remove debris and level the site for garden installation.

3.1.2 Install or repair fencing and access paths
Ensure safe and accessible entry to the garden area.

3.2 Garden Construction

3.2.1 Build raised garden beds
Construct durable beds for community planting.

3.2.2 Install irrigation system
Set up water lines and drip irrigation for sustainable maintenance.

3.2.3 Deliver soil and compost
Provide nutrient rich materials for planting.

3.3 Community Planting

3.3.1 Organize volunteer planting days
Coordinate community participation in initial planting.

3.3.2 Plant initial crops
Begin cultivation of vegetables, herbs, and flowers.

3.3.3 Set up maintenance schedule
Establish a volunteer rotation for ongoing care.

4.0 Administrative and Program Development

4.1 Staffing and Volunteer Recruitment

4.1.1 Recruit educators and program staff
Identify and hire qualified personnel for educational and support programs.

4.1.2 Recruit volunteers for pantry and garden
Engage community members to support operations.

4.1.3 Conduct background checks and onboarding
Complete required screenings and orientation.

4.2 Program and Partnership Development

4.2.1 Finalize partnership with Parks and Recreation
Confirm collaboration for youth and family programming.

4.2.2 Finalize partnership with Kansas City Public Library
Establish joint programming for literacy and community education.

4.2.3 Develop curricula for job training and community education
Create structured learning materials for program delivery.

4.2.4 Coordinate donation drives
Organize community contributions for pantry and clothing closet operations.

4.3 Operational Readiness

4.3.1 Develop policies and procedures
Create operational guidelines for all program areas.

4.3.2 Create safety and emergency plans
Prepare protocols for emergency response and risk mitigation.

4.3.3 Prepare opening day operations plan
Finalize staffing, logistics, and program schedules for launch.

5.0 Project Closeout

5.1 Grand Opening

5.1.1 Coordinate opening event
Plan and execute the public launch of the facility.

5.1.2 Launch job center and programming
Begin delivery of workforce and educational services.

5.1.3 Launch pantry and closet
Open food and clothing distribution services to the community.

5.1.4 Celebrate first garden harvest
Host a community event marking the first successful growing cycle.